## Progress Report
Progress Report
WO #10 "Best Practices for the Design, Evaluation and Quality Control of High Percentage RAP Mixes"
Contract |  | Project |  | Month of | Vendor Name |  |  |  |  | Date
4400008014 |  | PSU WO 10 |  | August 2014 | The Pennsylvania State University |  |  |  |  | 2014-08-27
Federal ID No. |  | Vendor SAP No. |  | Project Amount | Billed to Date |  |  | Percentage Billed
24-6000376 |  | 141597 |  | 55694
Task | Deliverable | [7 empty] | Due |  | Completed
1 | Review current PennDOT practices and specifications of RAP usage | [7 empty] | 2014-09-02
2 | Review/select nationally developed practices for high percentage RAP | [7 empty] | 2014-10-01
3 | Incorporate the changes into PennDOT publications | [7 empty] | 2015-04-01
4 | Finalize the changes in PennDOT publications | [7 empty] | 2015-06-01
5 | Develop an Implementation Plan | [7 empty] | 2015-06-01
6 | Draft final report | [7 empty] | 2015-06-01
7 | Final report | [7 empty] | 2015-06-30
Task | Accomplishments This Month |  |  |  |  | Activities Planned For Next Month
1 | Completed review of PennDOT publications. Provided a tabulated form of reviewed documents. Send the information to PennDOT. |  |  |  |  | Make any necessary changes to reviewed documents based on PennDOT comments.
2 | Began review of NCHRP 752 report and relevant documents. |  |  |  |  | Complete review of external documents and provide a report.
3 | No Activity |  |  |  |  | No Activity
4 | No Activity |  |  |  |  | No Activity
5 | No Activity |  |  |  |  | No Activity
6 | No Activity |  |  |  |  | No Activity
7 | No Activity |  |  |  |  | No Activity
Principal Investigator Comments
I certify that the above is correct and just. |  |  | Signature:
|  |  | Mansour Solaimanian |  |  |  | 2014-08-27 |  | 813-863-1903